## ProjectComplexity-v2.1
i3PM Project Complexity Assessment for Product Development Projects
v2.1
Project Name
BPM or POC (N/A if not yet assigned)
Project Manager (N/A if not yet assigned)
Project Management Methodology
Phase
Date
The Project Complexity is calculated based on the answers provided to the questions below. Please answer all of the questions to obtain the complexity rating.
Project Complexity Determination
| EAC Cost ($K) | Project Filter Score | Project Complexity
| < 250 | 15 - 35 | Low
|  | 36 - 60 | Medium
| 250 - 2500 | 15 - 35 | Medium
|  | 36 - 60 | High
| > 2,500 | any | High
| Cost for This Project |  |  |  | EAC for this Project ($K)
|  | Small | Medium | Large |  | Definition | Notes about this Project
| EAC Cost ($K) | < 250 | 250 - 2,500 | > 2,500 |  | EAC: Estimate at Completion of the Project: Planning to end of Deployment (all phases, all years). Include internal & license costs.
| Score for This Project |  |  |  | Score For This Project
|  | 1 | 2 | 4 |  | Definition / Notes | Notes on this Project
Scope | Number of Users | < 100 | 100 - 2,500 | > 2,500 | 4 | Average number of people connected per month when project is fully deployed.
| Business Units Impacted | 1 Function, Value Stream, and/or Business Line | 2 Functions, Value Streams, and/or Business Lines | > 2 Functions, Value Streams, and/or Business Lines | 4 | Functions: Operations, Manufacturing, Personnel, Financial, Legal, QHSE, etc.
| Certainty of Scope | Clear, fully defined, agreed objectives with low potential for scope creep | Some uncertainty of scope | Scope may require major changes during the project | 1 | What is the level of certainty that the scope will be stable or change?
| Project Duration | < 6 months | 6-12 months | > 12 months | 1 | How long the project is expected to last, based on completing the scope/requirements defined in the project charter?
Technical Requirements | Solution Complexity | Commercial Off The Shelf (COTS) solution - No gaps / No customization | COTS using lowcode/no-code capabilities to configure the product and fill gaps necessary to address business needs | The solution requires customizations to COTS, new technology development and/or new process definition | 2 | Degree to which the project requires custom software or processes. **Customizations of Commercial Off The Shelf solutions to address gaps are highly discouraged.**
| Number of Integrations | 0 - 1 | 2 | > 2 | 1 | Exclude Authentication and Authorization. Include potential integration points with other business functions.
| Data Availability/Quality | The project team have full knowledge of quality of data, and data is available | The project team does not know the data quality and/or does not have access to the data, but has established decision points in the schedule for acceptance criteria for deliverables quality and availability | The project team does not have access to the data and/or does not know the data quality, and will establish this understanding during the project | 1 | Have the sources of external data been identified, is the quality of the data known, and can the data be accessed?
| Data Accessibility | No requirements to share data downstream | Data to be made available via the Data Lake | Data to be made available via CIM | 1 | Will this become a source of data for another business system?
| Availability | Active workaround exists, no special requirements | Workaround exists if not available but heavy manual effort | No Workaround. High availability required. | 2 | Up-time, e.g. 99.5%.
Resources | Subject Matter Expert Availability | Subject matter expert will be assigned full time | Subject matter expert will be assigned, but < 50% | Subject matter expert will not be assigned | 1 | Extent to which subject matter expert is readily available to the project team.
| Project Management | Project manager is assigned now | Project manager will be assigned before the Project Charter is written | Project manager will not be assigned prior to implementation start | 1 | Extent to which project management role is staffed during planning, requirements collection and analysis, and design.
Business Case | Business Case | Internal efficiency | Operational efficiency or cost impact | Large operational efficiency or cost impact; <or> legal requirement; <or> business critical (in disaster recovery application set) | 2 | The nature of the primary business motivation, and degree of risk and reward, for the project.
| Business Benefits | Very well defined and quantified | Defined but not quantified | Not clearly defined | 1 | The precision with which the business benefits or value proposition are known, both hard and soft savings.
Sponsor | Sponsorship | Single Business Unit or Function | Primary Business Unit or Function with other secondary stakeholders | Shared among 2 or more Business Units or Functions | 1 | The number of senior decision makers who define the project and must approve the results.
Change | Business Change Management | GeoUnit | Function across the entire Basin | Enterprise Global | 4 | The effort to fully deploy the solution, train the users, and achieve routine operation.
| Total Score for this Project |  |  |  | 27
Question Scores
1
2
4
Complete the Complexity Assessment based on the known scope and requirements of the project. This information will be used to determine the governance processes and deliverables required.
Please review the results with your PMO.
Note on C14: EAC = Estimate at Completion

## RevisionHistory
Version | Release Date | Author | Changes